## Sheet1
Fota Feature List & Release Plan
TASK ID | Feature | Description | Delivery Plan | Status | Note
1 | Build Up IAR Project With Boot & APP | Build Boot/APP and Generate seperated *.bin file of BOOT & APP with Specific Signature | 2019-08-08 | IN PROGRESS
|  | Start up at Boot , run to APP ( Fixed Address , no swap yet ) | 2019-08-09 | NOT START | This First Delivery Day depend on when I Got the Hardware. If was delay , all following task delivery day will be shifted
2 | UART HAL | Tx Data with configurable Baudrate to PC | 2019-08-10 | NOT START
|  | Rx Data with configurable Baudrate from PC | 2019-08-10 | NOT START
3 | TIMER HAL | Able to Create/Start/Stop Software timer, with Callback when expired | 2019-08-11 | NOT START
4 | MCU HAL | Able to Reset Device in App & start run from Boot | 2019-08-11 | NOT START
5 | Flash HAL | Able to Erase/Program/Read at specific Address | 2019-08-12 | NOT START | OFF from 13 to 18/8/2019 , No Plan for this Period
6 | PC Script | Python script that support consume *.bin file , Verify Software Signature, Identify Boot or APP . | 2019-08-19 | NOT START | TASK ID 6 & 7 will be done in paralell. Because I have one another people that work on PC APP
|  | Send command/data to FW Upgrade device according to FOTA Protocol | 2019-08-19 | NOT START
7 | FOTA protocol | Support communication Protocol with PC APP as defined in Sequence diagram, with Package checksum , Package ID … ( BUT NO SAVING ANY DATA TO FLASH YET ) | 2019-08-21 | NOT START
|  | Error Handling : Lost message timeout/ Duplicated package handling | 2019-08-21 | NOT START
8 | FOTA Storage | Able to Read/Write APP Info, Identify APP SLOT ,swap Active App slot, Read/Write Software version | 2019-08-22 | NOT START
|  | Erase/Program into Inactive App slot or Boot area with the Firmware receive via FOTA Protocol | 2019-08-24 | NOT START
9 | BOOTLOADER | Able to use Fota Storage to Read/Write APP Info Area, Perform APP checksum, Swap Active APP | 2019-08-25 | NOT START
|  | Decide to Start Which APP Slot | 2019-08-26 | NOT START
10 | INTEGRATED TEST & RELEASE | Integrated Test & Release | 2019-08-27 | NOT START
NOT START
IN PROGRESS
TESTING
DONE